## Sheet1
Story | Task | Estimate min (hr) | Estimate max (hr) | Actual | Comment
Initial Setup | Project Scaffolding | 0.5 | 1 | 0.5 | Next.js Setup, Typescript configuration, folder structure
| Database Setup | 0.5 | 1 | 0.5 | PostgreSQL setup, Prisma schema, initial migrations
| Development Environment | 0.5 | 1 | 0.5 | ESLint, Prettier, VS Code Config, Git setup
| Environment Configuration | 0.5 | 1 | 0.5 | Environment Variables, API Keys, Documentation
Core Features | UI Framework Integration | 0.5 | 1 | 0.5 | Mantine Setup, theme configuration, base comments
| API Integration | 0.5 | 1 | 1 | Groq API Client, error handling, rate limiting, test
| Database Models | 0.5 | 1 | 1 | Experiment and response models, migrations
| Parameter Management | 1 | 2 | 1 | Parameter Checking, Validation
| Basic Experiment Flow | 1 | 2 | 1 | Prompt Input, Parameter selection, Response handling
Metrics | Coherence Scoring | 2 | 3 | 2.5 | Sentence analysis, flow measurement, normalization
| Vocabulary Analysis | 2 | 3 | 3 | Word diversity, sophistication measurement
| Length Metrics | 2 | 3 | 2 | Response length analysis, thresholds
| Readability Scoring | 2 | 3 | 2 | Flesch-Kincaid implementation, grade level analysis
| Repetition Detection | 1 | 2 | 1 | Pattern detection, penalty calculation
UI/UX | Experiment Form | 0.5 | 2 | 0.5 | Parameter controls, validation, responsive design
| Results Display | 2 | 3 | 1.5 | Response cards, metric visualization
| Export Features | 1 | 3 | 1.5 | CSV/JSON export, data formatting
| Loading States | 0.5 | 2 | 0.5 | Progress indicators, skeleton loaders
Documentation | Code Documentation | 1 | 2 | 0.5 | Code comments, Typescript types
| User Documentation | 1 | 2 | 1 | README
| Developer Docs | 1 | 2 | 1 | Setup Guide, Developer Guide, Architectural Guide
Refactoring | Type Checks | 1 | 2 | 1 | Check ESLint and type issues
| Final Styling | 2 | 3 | 1 | Beautify application with responsive UI
| Performance Optimization | 2 | 3 | 0.5 | Optimize performance
Test | User Test | 1 | 2 | 1 | Test manually
| Total | 27.5 | 51 | 27